| SKSQ20 Set up and organise a costume department |  |
| --- | --- |

Overview

​This standard is about your ability to plan, set up and organise a costume department linked to a production.

This may involve recruiting department members, liaising with other departments, assessing available workspace and sourcing and setting up equipment

This standard may be applicable to costume supervisors, costume managers and costume assistants.

Performance criteria

You must be able to:

- ​confirm the costume requirements, production schedule and budget

- review the costume breakdown and identify resources required to store, distribute and maintain costumes

- identify and assess the space available considering security, confidentially and risk issues

- identify and recruit costume personnel with the required skills within budget

- consult with the designer and production staff and negotiate costume staff terms and conditions

- ensure the costume personnel are fully trained

- identify and source the equipment and tools required within the budget restraints

- identify and source the fabrics and materials required within the budget restraints

- organise the delivery of resources

- assemble, position and install equipment within the chosen area considering

- obstacles, hazards and safety conditions

- create a safe, functional and secure working environment

- identify the departments running and maintenance costs

- create and confirm the costume storage

- create and formalise a return process

- ensure adequate security measures are in place

- ensure the required insurance policies are in place

- communicate clearly with production staff and other relevant departments or individual

- ensure health, safety and environmental legislation and guidelines are in place and followed at all times

Knowledge and understanding

You need to know and understand:

- ​the requirements of the production and schedule

- the production budget and timescales at your disposal

- how to identify the crewing and skills requirements

- how to select and recruit members of the costume department

- how to effectively negotiate terms and conditions

- the roles, responsibilities and tasks required of the costume department

- equipment required to complete tasks  in the costume department, such as tagging guns, scissors, racks and pressing equipment  and how to use them safely

- facilities required within a costume department  e.g. running water, electricity

- required security measures

- department maintenance and running cost

- the cost implications involved in the loss or damage of items

- adequate insurance arrangements

- efficient costume booking, borrowing and returning processes

- legislative and regulatory requirements applicable to handling and storing hazardous materials

- the communication protocol with production staff and other relevant departments or individual

- statutory responsibilities under health, safety and environmental legislation and regulations

Developed by

ScreenSkills

Version Number

2

Date Approved

30 Mar 2021

Indicative Review Date

30 Mar 2025

Validity

Current

Status

Original

Originating Organisation

ScreenSkills

Original URN

SKSQ30

Relevant Occupations

Arts, Media and Publishing, Associate Professionals and Technical Occupations, Crafts, Creative Arts and Design, Media and Communication, Media Associate Professionals

Suite

Costume for Film, TV and Theatre Productions

Keywords

costume; wardrobe; department; manage; organise; production